## Gantt Chart
UK Oil Plc — Option 1 Gantt Chart (PERT)
Expected time = (O + 4M + P) ÷ 6 · Red bar = critical path (no float) · Blue bar = has float · Months counted from the start of Activity A
Blue numbers = durations from the Assessment Brief (change them and the chart redraws).
Act | Activity | Depends on | O | M | P | Expected (months) | Start month | Finish month | Latest start | Latest finish | Float (months) | Critical? | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
A | Geological Study (already completed) | — | 12 |  |  | 12 | 0 | 12 | 0 | 12 | 0 | YES
B | Technical Evaluation | A | 2 | 4 | 10 | 4.6667 | 12 | 16.6667 | 12 | 16.6667 | 0 | YES
C | Financial Evaluation | A | 3 |  |  | 3 | 12 | 15 | 13.6667 | 16.6667 | 1.6667 | no
D | Board Consideration | B & C | 1 | 2 | 3 | 2 | 16.6667 | 18.6667 | 16.6667 | 18.6667 | 0 | YES
E | Bidding Process | D | 1 | 2 | 8 | 2.8333 | 18.6667 | 21.5 | 18.6667 | 21.5 | 0 | YES
F | Safety Report | E | 1 | 4 | 7 | 4 | 21.5 | 25.5 | 21.5 | 25.5 | 0 | YES
G | Hire & Training of Labour | E | 1 | 2 | 3 | 2 | 21.5 | 23.5 | 23.5 | 25.5 | 2 | no
H | Site Preparation | F & G | 3 | 5 | 10 | 5.5 | 25.5 | 31 | 25.5 | 31 | 0 | YES
I | Delivery of Material | H | 1 | 2 | 3 | 2 | 31 | 33 | 33 | 35 | 2 | no
J | Delivery & Construction of the Oil Platform | F & H | 2 | 4 | 6 | 4 | 31 | 35 | 31 | 35 | 0 | YES
K | Pre-Sale Drilling & Production | I & J | 1 | 3 | 8 | 3.5 | 35 | 38.5 | 35 | 38.5 | 0 | YES
L | Sales (ongoing for 25 years) | K |  |  |  | 300 | 38.5 | 338.5 | 38.5 | 338.5 | 0 | YES
Months until first oil (Activity L starts) | [5 empty] | 38.5
…of which still to go after the completed Activity A | [5 empty] | 26.5
Critical path | [5 empty] | A-B-D-E-F-H-J-K-L
Activity F (Safety Report) float | [5 empty] | 0
Activity F has no float, so the brief's warning about a shortage of safety engineers is a direct risk to the start date. C, G and I can slip by their float without delaying first oil.

## Rights Ratio
UK Oil Plc — Rights Issue to raise £300,000,000
Week 3 slide formulas. Change the yellow cells and everything updates.
The numbers (Assessment Brief)
Amount to raise (£) | 300000000 | Your target.
Existing £1 ordinary shares | 1000000000 | Brief: £1,000M of £1 shares.
Market price per share (£) | 3.5 | Brief.
Nominal value per share (£) | 1 | Brief: £1 shares.
Rights ratio: 1 new share for every N held. N = | 4 | Pick the ratio.
Issue price per new share (£) | 1.2 | Bank says £1.00–£1.25 will succeed.
Bank fees (£) | 5000000 | Brief: £5M whatever the size.
The answers (Week 3 slides 28–34)
New shares issued | 250000000 | 1,000,000,000 ÷ 4
Cash raised (£) | 300000000 | 250,000,000 × £1.20
Raises the £300M? | YES
Value of the right (£) | 2.3 | £3.50 − £1.20
Over the brief's £1.00 minimum? | YES
Share premium (£) | 50000000 | (£1.20 − £1.00) × 250,000,000
TERP — share price after the issue (£) | 3.04 | (4 × £3.50 + £1.20) ÷ 5
Cash left after bank fees (£) | 295000000
Which ratio works? (price needed to raise exactly £300M)
Rights ratio | Issue price needed | Inside £1.00–£1.25?
3 | 0.9 | NO
4 | 1.2 | YES
5 | 1.5 | NO
6 | 1.8 | NO
Only 1-for-4 (at £1.20) is inside the bank's range.